## Slide 1: Project “Ex-ante evaluation of programming documents and strengthening evaluation capacity for EU funds post-accession” (EUROPAID/130401/D/SER/HR)
Programme Evaluation Activities:
Outcomes & Lessons Learned
A Presentation of Component I
Zagreb, 23 April 2013
Dr. Antony Mousios, TL-KE1
VISIBILITY EVENT
From IPA to Structural Funds in Croatia:
Lessons from and for Evaluation

## Slide 2
Component I Evaluation Activities

## Slide 3: Objectives:
3
Improve overall quality of structural funds 2007-2013 programming in Croatia by conducting interim and ex-ante evaluations that assessed:
  the implementation progress of counterpart Operational Programmes under IPA Components III & IV;
  prospectively the impact of the NSRF and four related Cohesion policy OPs, and of the programming document under the EU Common Fisheries Policy for the 2007-2013 period.
Review & appraise the strategic framework for the next period by:
  preliminary assessments of programming intervention logic for the 2014-2020 EU financial perspective.

## Slide 4: Expert Resources:
NKEs were deployed after transparent selection procedures, based on pre-defined criteria, including professional qualifications and work experience
NAME | LEVEL/FIELD OF EXPERTISE
Dr. Antony Mousios | Team Leader, NSRF, Evaluation Methods
Dr. Marie Kaufman | NKE, Environment
Mr. Jakub Štogr | NKE, Transportation
Mr. Jan Helbich | NKE, Human Resources Development
Mr. Tamas Lunk | NKE, Regional Competitiveness
Mr. Michal Musil | NKE, Fisheries

## Slide 5: Outputs:
Programme | Interim Evaluation | Ex- Ante Evaluation | Pre-assessment
NSRF 2013 |  | X | 
OP Environment 2007-13 | X | X | 
OP Transport 2007-13 | X | X | 
OP Human Resources Development 2007-13 | X | X | 
OP Regional Competitiveness 2007-13 | X | X | 
OP Fisheries 2013 |  | X | 
Intervention Logic 2014-20 |  |  | X

## Slide 6: Core Analytical Tasks: (1/2)
Appraisal of socio-economic, sectoral & of SWOT analysis;
Appraisal of internal and external consistency of the strategy /intervention logic underlying the NSRF’s/OP’s main objectives with relevant national and EU strategic documents;
Appraisal of appropriateness and clarity of indicators & their relevancy to specificities of interventions;

## Slide 7: Core Analytical Tasks: (2/2)
Assessment of Priority Axes and key areas of intervention;
Analysis of expected impacts and their alignment & consistency with the budgetary allocation over the objectives;
Assessment of quality and appropriateness of the programme management structures and monitoring arrangements currently in place, as well as foreseen;
Assessment of coherence and of lessons learned – in programming, implementation, absorption and capacity needs – from the experience under previous EU assistance.

## Slide 8: Analysis Instruments: (1/2)
Use/processing of secondary source data:
  Desk-based review of background statistical data, Programme texts, other policy documentation.
Use/processing of administrative data:
  Information relating to the OP’s administration, main sources include the IPA/SF’s monitoring system, Annual Implementation Reports, Organisational Development Strategy & Workload Analysis.

## Slide 9: Analysis Instruments: (2/2)
Stakeholder consultation:
  Through an interactive and iterative process between evaluators and programming authorities (interviews/meetings with MRDEUF & relevant Operating Structures).
Logic models:
  Per OP, linking contexts, assumptions, inputs, intervention logics, implementation chains with outcomes and results.

## Slide 10: Component I Evaluation Findings

## Slide 11: NSRF (1/3)
Appraisal of needs assessment & SWOT analysis:
  both have relevant scope & use qualitative and quantitative data supporting conclusions of the analysis in a convincing manner;
  are addressing all key macroeconomic parameters of Cohesion policy in Croatia, but need to update 2012 data on GDP contraction & deteriorating labour market conditions;
  enable the needs of particular stakeholder groups, and regions to be differentiated and addressed, and have a European perspective making issues & conclusions EU-comparable.

## Slide 12: NSRF (2/3)
The strategic orientation/intervention logic are very elaborately structured and clearly explained and the NSRF’s external coherence to EU & to pertinent national policies is documented by its design process and content.
But the statements of intent at the level of overall /strategic objectives are very broad and ambitious in nature compared with the select and narrow focus of interventions under the OPs, thus, streamlining and harmonising their content are recommended.

## Slide 13: NSRF (3/3)
The elements of the indicator system for the first two Thematic Priorities are well developed, manageable and useful. Aggregated indicators that cannot be directly attributable to NSRF interventions under TP 3-4 need refinement.
The institutional set-up for the NSRF includes a 3-level and multi-institutions management structure provides continuity, but clear guidance on improving project readiness during the programming process is required, to be combined with securing sufficient administrative capacity.

## Slide 14: OP-level Observations (1/4)
IPA, as transitional assistance linked to accession preparation that aimed mainly at institution building, is proving to be a positive organizational learning experience for coordinating and line institutions, facilitating future prospects in Croatia for better programming and management practises under structural funds.
Nonetheless, the interim evaluations of IPA OPs highlighted gaps/weaknesses in efficiency due to:
  Limited strategic programming (insufficient prioritisation, too focused on projects, not sufficient strategic/sectoral approach).

## Slide 15: OP-level Observations (2/4)
  Long gap (2-3 years) from programming to actual implementation due to delays linked to the fulfilment of project conditionalities (technical documentation, procurement procedures).
  Weak administrative capacity of beneficiaries, punctuated by high staff turnover at all levels and positions throughout OS.
To enhance the performance of on-going IPA assistance at this late stage and improve its prospects for impact and sustainability, upgraded administrative/operational processes needed to be embedded in the beneficiaries operational framework.

## Slide 16: OP-level Observations (3/4)
Overall positive judgement of 2007-2013 programming documents by the ex-ante evaluation, ensuring that these meet the EU standards for content & quality.
The identified needs, driving forces and causes of disparities per sector do play the expected prominent role in the definition of OP strategies & intervention logic.
The OPs do reflect the objectives of Cohesion policy, as well as the Common Fisheries Policy, further elaborated, refined and adapted to national/sectoral context.

## Slide 17: OP-level Observations (4/4)
In all 5 OPs, full intervention logics (general objectives – specific/operational objectives – expected results) are included in a structured way.
The EU common baseline and impact indicators are applied to a consistently high level of completeness & homogeneity.
The overall balance between Measures is fairly appropriate with regard to needs identified & established objectives.
Due to the OP’s limited implementation period & scope of financial allocations, significant progress in addressing all development needs identified is unlikely. Planned interventions should be regarded instead as the initial phase of policies that in the 2014-20 programming period will benefit from substantially higher concentration of resources, enabling the achievement of long-term, strategic goals.

## Slide 18: 2014-20 Intervention Logic
Our initial assessment of programming of the EU SF assistance for the 2014-2020 financial perspective acknowledges the structured contributions of a functional thematic coordination network, justifying investment actions on EU & national strategies & enhancing the national ownership of the eventual Partnership Agreement.
The formulated programme intervention logic & strategy is being systematically defined in terms of objectives, results, outputs plus their indicators and baselines, forming a sound basis for the implementation strategy.
At the same time, our analysis has pinpointed some critical areas especially on documenting proposed actions & development targets, requiring additional clarifications and further elaboration by the relevant bodies.
Notes: t

## Slide 19
I thank you for your attention