Highlight Report

## Purpose: The highlight report updates the project sponsor and the project board about the project’s progress to date.  It also provides an opportunity to raise concerns and issues with the Board, and alert them to any changes that may affect the project.

| Project Name: | Academic year reform |  |  |
| --- | --- | --- | --- |
| Project Number: |  | Reporting Period: | 4 October 2014 – 14 November |
| Project Sponsor/Executive: | Paul Kelly |  |  |
| Project Manager: | MTT | Date prepared: | 18 November 2014 |

Distribution – this document was distributed to:

| Name | Date | Version |
| --- | --- | --- |
| Paul Kelly |  |  |
| Simeon Underwood |  |  |
| Project board members |  |  |

# Current Project Status:

# General Headlines:

- The project is currently on track as the first stage of detailed implementation planning in departments begins producing outcomes; namely, an indication of the extent to which departments will make use of the LT0 2016 exam period; and how they plan to organise their taught provision over the new 11-week teaching terms.

- The deadline for departments to indicate their intention to hold LT0 exams is 28 November 2014.  Registry will then develop draft LT0 and ST 2016 exam schedules.  Based on LT0 demand (including the factoring in of examination constraints around when students can sit papers relative to other papers), we will be able to determine whether, and the extent to which, rooms currently booked for LT0 exams can be released for the use of other School functions (e.g. executive teaching).  We will have made these determinations before Christmas break 2014.

- The need to determine the extent to which rooms currently booked for LT0 2016 exams can be released is particularly pressing for the EMPA (i.e. in light of commercial pressures).  This issue raises a matter of principle about allocating space when there are multiple demands for its use.  The Director of Estates is in the process of developing a 'space allocation policy' to help make determinations in such cases.

- Determining the LT0 and ST 2016 exam schedules will also allow the Registry and Assessment Regulations teams to begin evaluating the regulatory changes necessary under the new academic year structure, e.g. to the degree regulations governing student progression/completion.

- This work on updating the regulatory framework to support the terms of the new academic year structure needs also to dovetail with a) departmental determination of local assessment principles/approaches, i.e. School-level regulations need to support and permit departmental innovations in assessment;  and b) the outputs of the working group on feedback.  On a) we will need to establish the timeline departments are working to (i.e. for the development of their statements of assessment principles/approaches) so that we are clear about deadlines for making amendments to regulations.  One idea for ensuring that such statements are developed in a timely way, and so that they inform regulatory updates, is to bring together departmental teaching committee chairs/deputy HoDs teaching to discuss ideas/best practice, and to try and accelerate departmental thinking (i.e. so we know what they’re doing in time to make necessary regulatory changes).  This approach will allow the regulatory changes arising out of the new academic year structure, departmental statements on assessment principles/approaches and the outputs of the feedback working group to be put to the May 2015 Academic Board meeting, the same meeting to which AB/5 – which gave rise to departmental determination and the working group – stated that the working group would report its findings and recommendations.

- If departmental ‘statements of assessment principles’ result in changes to how some courses are assessed (which seems certain in at least some cases), or if changes to course assessments arise out of AYR planning, these need to be submitted to USSC/GSSC by May 2015 to be included in the 2015/16 Calendar.

- The project board has identified the following broad issues to be addressed as part of any work to amend degree regulations and supplementary rules/guidelines: 1) exam setting/scrutiny processes; 2) requirement that LT0 exams are ‘normally’ marked by e.g. LT4?, and that 3) provisional results are made available; or that an earlier round of sub-board meetings are held.

- Once LT0 exam demand is known, we will also be able to assess the necessary logistical support, in terms of setting the required rooms up in 'examination' style before the School closes for Christmas 2015; and converting them back to 'teaching' style over the weekend after LT0 2016.  There may be a cost implication around bringing in temporary portering staff.

- When determining LT0 exam capacity, we need to look at the various lengths of LT0 across different years, depending on when Christmas/NY fall in the calendar.  The reduction of LT0 by a day might mean that in some years, we could not hold LT0 exams in courses that have been examined in the earlier exam period in previous years.  If demand for LT0 exams gets to the level such that this scenario arises, we will need either to develop a policy for determining which courses get to 'hold on' to their LT0 exam slots (and to develop operational arrangements that ensure assessment arrangements are updated in course guides according to the normal updating schedule); or hold some LT0 exams at alternative times (e.g. evenings of LT1); or hold LT0 exams during LT0 but in alternative venues.  There will be a cost associated with this final option, and probably a significant one.

- Once the draft ST 2016 exam schedule is complete (before Christmas break 2014), we will be able to plot out the timing of sub- and School Board of Examiners meetings.  We will then be in a position to determine whether the timing of the Graduation Ceremonies can be brought forward.  Whether the timing of the ceremonies is in fact moved will be a matter for the project executive.

- Departments have been asked to indicate how they will use the extra term-time week by mid-January 2015 (e.g. WK6 reading weeks, and – if so – whether they will run any structured learning activities).  A firm deadline of the end of January will be given, after which time WK6 teaching space will be released for the use of other School functions (i.e. where departments have indicated that they do not need all or some of their allocated teaching space in WK6).  Graduate Open Evening has signalled a significant demand for rooms during MT WK6 2015 (4 November).

- Met with Director of Residential Services (Ian Spencer) and Director of Facilities Management (Allan Blair) about communications with cleaning and catering staff on 'term-time only' contracts.  This meeting was in response to Unison requests for Town Hall style meeting with contracted out staff.  We will produce a 'fact sheet', setting out the revised academic year structure, and emphasising that the demand for the services this category of staff provide is independent of core teaching, i.e. owing to ancillary programmes/activities.  We will then offer to hold a Town Hall meeting in early February, i.e. after departments have indicated the extent to which they will use their allocated teaching space in WK6.

# Actions and outputs for the last period:

- Clarification of reading week timing.

- At time of writing, departments have confirmed 31 courses to be examined in LT0 2016; GV has indicated that it is ‘highly probably’ that it will hold LT0 exams for some of its MT half-units; and we are waiting to hear by 28 November from DV, EH, GI, GY, HY, LL, MC, MY, PS, and SA.  Please see attached spreadsheet for further details.

- Anthropology confirmed that it will hold a WK6 reading week and will not be making use of its teaching space allocation at that time.

- Sociology confirmed that all UG students will have a ‘pure’ WK 6 reading week, i.e. students will be encouraged to consolidate learning and work on assessments; individual PGT conveners will determine whether to hold WK 6 learning activities linked with dissertation workshops.

- Confirmation from Maths and Economics that they will deliver lectures in WKs1-10 and classes/seminars in WKs 2-11.

# Actions and outputs for the next period:

- Departments to finalise courses to be examined in LT0 2016 by 28 November 2014.

- Registry to develop draft LT0 and ST 2016 exam schedules before Christmas break 2014.

- Release of rooms currently held for LT0 exams but which turn out not to be needed by Christmas break 2014.

- Departments to finalise use of teaching space allocation during MT WK6 2015 and LT WK6 2016 by 30 January 2015.

- Release of rooms currently held for WK6 structured learning activities by early February 2015.

- ‘Fact sheet’ for staff on term-time only contracts to clarify what the new academic year will look like by 28 November 2014; Town Hall meeting by early February 2015.

- Work to begin on regulatory amendments by early Lent Term 2015; final recommendations to 13 May 2015 Academic Board.

Don't lose sight of…

- Progress with aligning IMT business systems and the procedures they support with the new academic year structure.

- GLPD’s progress in assessing impact on committee cycle, number and timing of meetings.

- Start-of-year activities, e.g. earlier admissions/registration (especially for pre-sessional students); availability of School services for early arrivers, e.g. catering, Library, halls, moving Orientation forward by a week.

- Issue of ST sabbatical – although the structure of the year makes it possible to front or back load teaching such that research can take place in ST without formal sabbatical, this model won’t work for smaller units, whose staff will regard taking formal sabbatical leave in ST as undesirable, given the shorter period.

# Risks:

# Current risk(s) for highlight are:

| No. | Description | Risk Owner | Countermeasures & Progress | Current status |
| --- | --- | --- | --- | --- |
| 1 | Lack of departmental engagement with planning process | MTT | Progress monitoring to pick up pace of planning across departments; TLC support/guidance with practicalities of structured learning activities during ‘reading week’. | Green |
| 2 | Same information requests made of departments by different projects | MTT/Zoë Saunders-White | RATS project member kept informed of developments on relevant AYR project work streams; vice versa. | Green |
| 3 | Ongoing industrial action could affect LT0 exam marking | S Underwood | DMT to monitor | Amber |

# Issues:

# Current issue(s) for highlight are:

| No. | Description | Issue Owner | Countermeasures | Current status |
| --- | --- | --- | --- | --- |
| 1 | Need to begin realignment of School’s business systems under new academic year structure | Ron Riley | This will be kick-started by Ron who has now joined the project board. | Green |
| 2 | Need to carefully manage and possibly limit the number of courses to be examined in LT0 in light of the varying number of days in LT0 across different calendar years. | Registry | We will have a firmer grasp on capacity after the initial LT0 2016 draft examination schedule is produced before Christmas break 2014. | Green |

# Lessons Learned in this Period:

| No. | Description |
| --- | --- |
| 1 | Need to be consistent about permitted timing of reading week, i.e. Week 6 only. |

Papers due to Agenda Committee by 22 April 2015 for its 30 April meeting.  Academic Board meeting will be 13 May 2015.