Highlight Report

## Purpose: The highlight report updates the project sponsor and the project board about the project’s progress to date.  It also provides an opportunity to raise concerns and issues with the Board, and alert them to any changes that may affect the project.

| Project Name: | Academic year reform |  |  |
| --- | --- | --- | --- |
| Project Number: |  | Reporting Period: | December 2014 – March 2015 |
| Project Sponsor/Executive: | Paul Kelly |  |  |
| Project Manager: | MTT | Date prepared: | 15 April 2015 |

Distribution – this document was distributed to:

| Name | Date | Version |
| --- | --- | --- |
| Paul Kelly |  |  |
| Simeon Underwood |  |  |
| Project board members |  |  |

# Current Project Status:

# General Headlines:

- First draft of regulatory amendments is currently with a working group the Academic Board established for the purpose at its 26 February meeting.  The group's revised draft will be put to the VCAB for approval (i.e. on the Board's behalf) w/b 20 April.  A summary of the regulatory changes (already drafted) will be submitted to the Academic Board Agenda Committee by 23 April for the 13 May Academic Board meeting.

- The amended regulations are student-facing and include: the Conditions of Registration, General Academic Regulations, Degree Regulations (Certificates, First Degrees, Diplomas and Masters) and Classification Schemes.  Other regulatory documents are outside the scope of this review, but the annual process by which the School updates its overall suite of regulations includes guidance for owners of 'other' regulations to be mindful of the need to calibrate them to the timings of the new year.

- The proposed regulatory changes are mainly driven by an effort to make the framework more efficient and to reduce redundancies.  The main change arising from the academic year structure relates to clarifying when students can re-sit assessments in light of the introduction of LT0 exams, e.g. ‘if a student is required to re-sit an examination or defers an attempt at an examination, the next opportunity will normally be in the next academic year during the equivalent examination period as the original failed or deferred attempt’.

- Early sight of several draft departmental Assessment and Feedback Statements has confirmed that no regulatory amendments will be necessary to accommodate their contents.  Some operational changes to the ARD's 'Instructions for Examiners' might be necessary, but these can be made outside of the formal committee cycle.

- Need to amend the timing of the process for appointing/re-appointing external examiners.  Registry has this in hand.  In reviewing the current arrangements, Registry has identified some inequity in the payments different externals receive, and propose that UG and PGT externals are paid on a course-by-course basis (at the moment, PGT externals are paid by the programme, which results in many being either over or under paid for their work).  This is likely to require an increase to the budget from which externals’ fees are met.  Registry is working on a figure.

- Need to obtain outstanding course-level information from departments about their intention for reading weeks.  There are two main drivers here: 1) Timetables needs this information so that it knows which rooms can be released in WK6 to other School users (e.g. Recruitment for Graduate Open Evenings and outreach activities; to the Summer School for an additional Executive Summer School stream); and 2) to inform incoming and continuing students about what they can expect during WK6 at the level of individual courses.  Obtaining outstanding course-level information from departments about their plans for WK6 will be the main priority of the remaining AYR implementation work for ST 2015.

- Departments have been advised to provide this information as part of a) the first stage of the new timetabling process, which has requested from them their 2015-16 teaching space needs; and a) the annual course guide review process.  The deadline for a) has passed, and the information provided was far from complete (possibly due to the understandable reasons that the timetabling system is new; and that departments might not yet have determined their WK6 plans at the individual course level).  To ensure that this information is available, MTT will write to departments (w/b 27 April) with a simple template asking for WK6 plans, e.g. whether courses will feature formal teaching in WK6, or a reading week; and if the latter, whether any learning activities will be scheduled.  Accompanying guidance will advise departments to ensure that their student-facing information sources (e.g. websites, handbooks, Moodle pages and post-offer information platforms) are updated in good time prior to the start of the 2015-16 academic year.

- The list of courses that will make use of LT0 2016 has been finalised and stands at 36 (11 UG courses, 25 PGT courses).  Registry has modelled the LT0 2016 exam schedule and has confirmed that it can deliver all exams involved in 4.5 days, starting in the afternoon of Monday 4 January 2016.

- 11 of the 36 courses are full-units, and so will feature a 'mid-term' in the LT0 exam period (i.e. the final examination will continue to be held in ST).

- The Registry will face challenges with scheduling LT0 2017 and LT0 2018 exams.  LT0 in those years will only be four days long (as opposed to five in 2016).  The School would either need to require students to sit exams on the January bank holiday; or at the weekend (or possibly both); or else hire external exam venues.  These options will also need to be considered if the School experiences growth in the number of courses that make use of the LT0 exam period (i.e. beyond EC’s phased introduction of LT0 ‘mid-terms’ for all of its courses).

- The 2016 Graduation Ceremonies will maintain their current timing – we need to give the Peacock two years’ notice of any change in the timing of the School’s use of the theatre.  Maintaining the ceremonies at their current time while also ending the exam period earlier will improve a) the integrity of the mark-processing arrangements, and b) the student experience (e.g. those students who do not complete are not currently informed until the day before their ceremony).  Maintaining the current timing of the ceremonies also allows Recruitment to hold on-site Open Days and outreach activities.

- By contrast, the Summer School would like to bring forward the ceremonies to accommodate an earlier Summer School start date.  Any decision to bring forward the 2017 ceremonies will need to be made by the start of June 2015.

- The Summer School would also like to introduce an additional stream of the Executive Summer School in MT6 2016.  At the moment, in the absence of complete information about departmental MT6 2015 plans, Timetables has insufficient information on which to base a decision about whether this additional ESS stream could be scheduled.  Timetables will have a better idea once it has complete MT6 2015 information at the course level, which will be by the end of ST 2015.  Even then, it is possible that individual course leaders might alter their MT6 2016 plans based on their MT6 2015 experiences, making the MT6 2015 timetable an imperfect basis for planning MT6 2016.

- Revision teaching.  The structure of ST 2016 will see ST1 held open for revision teaching, and exams held in ST2-7.  Some courses, however, currently have more than one revision teaching event scheduled (i.e. in ST1 and ST2).  Registry has been asked to model the ST 2016 exam schedule with the condition ‘exams for courses with revision events in ST1 and ST2 to be held no earlier than ST3’.  If it is possible to schedule all exams in ST when this condition applies (and if the School is happy with the pedagogic position that would see some students in ST2 attending revision teaching in certain courses and sitting exams in certain other courses), then it will be possible for the courses in question to maintain their two planned revision teaching events (though Timetables and Registry will need to be mindful of scheduling capacity in light of the future growth of courses with multiple revision teaching events).  If it is not possible to accommodate this scheduling condition, then TQARO will need to advise individual course conveners to hold one revision teaching event in ST1 only.

- Residences have amended student term-time contracts to reflect shorter arrangements of 30 and 38 weeks respectively.  50 week contracts remain unchanged. Start dates of student term-time contracts have been brought forward and harmonised to reflect the change in academic term date.  As part of the annual rent setting process, the overall change to the number of nights that students stay in term-time has been amended. This is also reflected in clear 2015/16 annualised rent calculations.  Publications – print and digital – that feature duration date and rent information have been amended to include changes (the exception to this is the 2015/16 UG and PG prospectuses which are confirmed 18 months prior to the relevant academic year). Information for events such as visit and open days has been amended. Partners providing accommodation, e.g., Zebra Housing Association, Urbanest, etc have been advised of changes.  Internally, changes to the academic year have been cascaded through team meetings to Front of House Manager, Catering, Residences Management Team and Wardens.

- The project board will monitor the implementation of the new academic year structure across 2015-16, and put an ‘issues and proposals’ report to Academic Board in ST 2016 (if necessary).

# Actions and outputs for the last period:

- Courses to be examined in LT0 finalised.

- Progress with departmental WK6 plans.

- Student-facing regulations amended (subject to 13 May Academic Board approval)

- Residences’ contracts amended; and relevant operational areas updated

# Actions and outputs for the next period:

- Project executive to take decision about whether to alter Presentation Ceremony dates by June 2015.

- Departments to indicate course-level plans for WK6 by end of ST 2015.

- Registry and Timetables to model whether revision teaching and exams can ‘fit’ into ST2, and whether current systems are capable of co-scheduling both activities, by end of ST 2015.

- Registry to finalise amendments to the process for appointing/re-appointing external examiners by end of ST 2015 (including details about budgetary impacts).

- Project Manager to develop concrete proposals for accommodating growth in LT0 exams (e.g. cost and other implications of holding exams at weekends, at external venues) by summer 2015.

- Departments to ensure that their student-facing information is up-to-date, e.g. webpages, student handbooks, Moodle pages and platforms for post-offer contact information, by summer 2015.

Don't lose sight of…

- GLPD’s progress in assessing impact on committee cycle, number and timing of meetings.

- Start-of-year activities, e.g. earlier admissions/registration (especially for pre-sessional students); availability of School services for early arrivers, e.g. catering, Library, halls, moving Orientation forward by a week.

- Issue of ST sabbatical – although the structure of the year makes it possible to front or back load teaching such that research can take place in ST without formal sabbatical, this model won’t work for smaller units, whose staff will regard taking formal sabbatical leave in ST as undesirable, given the shorter period.

# Risks:

# Current risk(s) for highlight are:

| No. | Description | Risk Owner | Countermeasures & Progress | Current status |
| --- | --- | --- | --- | --- |
| 1 | Lack of departmental engagement with planning process | MTT | Establishing course-level WK6 information will comprise main focus of ST 2015 implementation work. | Green |
| 2 | Same information requests made of departments by different projects | MTT/Zoë Saunders-White | RATS project member kept informed of developments on relevant AYR project work streams; vice versa. | Green |

# Issues:

# Current issue(s) for highlight are:

| No. | Description | Issue Owner | Countermeasures | Current status |
| --- | --- | --- | --- | --- |
| 1 | Need to begin realignment of School’s business systems under new academic year structure | Ron Riley | This will be kick-started by Ron who has now joined the project board. | Green |
| 2 | Presentation Ceremonies | Paul Kelly | Decision on whether to maintain current timing or bring forward, based on case/evidence provided by proponents of each position. | Amber |
| 3 | Future growth of LT0 exams | MTT, Registry | Need to develop proposals/costings for external venue hire. | Amber |

# Lessons Learned in this Period:

| No. | Description |
| --- | --- |
| 1 | Need to be consistent about permitted timing of reading week, i.e. Week 6 only. |
| 2 | Better/clearer communication and planning with projects whose remit overlaps with the AYR project, e.g. guidance could have been clearer on completing WK6 plans in the information requested by the web data collector. |