Highlight Report

## Purpose: The highlight report updates the project sponsor and the project board about the project’s progress to date.  It also provides an opportunity to raise concerns and issues with the Board, and alert them to any changes that may affect the project.

| Project Name: | Academic year reform |  |  |
| --- | --- | --- | --- |
| Project Number: |  | Reporting Period: | 14 July – 3 October 2014 |
| Project Sponsor/Executive: | Paul Kelly |  |  |
| Project Manager: | MTT | Date prepared: | 3 October 2014 |

Distribution – this document was distributed to:

| Name | Date | Version |
| --- | --- | --- |
| Paul Kelly |  |  |
| Simeon Underwood |  |  |
| Project board members |  |  |

# Current Project Status:

# General Headlines:

- The project is currently on track as it moves into the first stage of detailed implementation planning in departments and professional services.

- Further to the communications plan the project board agreed in July, departments have been advised to undertake planning for 1) the organisation of the extra term-time week (by January 2015); 2) use of the Lent Term ‘Week 0’ exam period (initial declarations of interest by early November 2014); and 3) timetabling their eMSc programmes.

- Project board members also received the communiqué setting out these points, for the purpose of cascading to colleagues in professional services.

# Actions and outputs for the last period:

- Conferences have aligned the School’s use of the Peacock Theatre with the new term dates under the revised academic year structure.  Person responsible: Rachel Ward

- TLC has written to HoDs outlining possible options for structured learning activities during reading weeks.  Person responsible: Neil Mclean

- Collaboration established with the Room Booking and Timetabling System (RATS) project.  Person responsible: Mark Thomson

- Departmental clarification sought on discretion to hold reading weeks or structured learning activities at times other than in Week 6.  In light of aim to improve student learning experience, it is open to departments to make the case to hold structured learning activities at times other than during Week 6 if e.g. their programmes are relatively ‘self-contained’ (i.e. taken only by students in the department, and will not therefore unduly impact other students) and clearly support the achievement of learning outcomes in the programme in question.  Person responsible: Mark Thomson

- Meeting with Unison reps, re: concern about diminished demand for the services staff on ‘term-time only’ contracts provide (e.g. catering, cleaning).  Request for ‘town hall’ meetings with staff.  Person responsible: Mark Thomson

- Confirmation from LSE Careers that its services will be realigned with the new academic year structure.  Person responsible: Jenny Blakesley

- USSC/GSSC advised to assess new course proposals to run next year for planned use of extra term-time week and Lent Term ‘Week 0’ exam period.  Person responsible: Mark Thomson

# Actions and outputs for the next period:

- Student Services to undertake a Lent Term 2016 ‘Week 0’ modelling exercise to determine 1) capacity/logistical requirements, and 2) required amendments to degree regulations.  This exercise to be informed by early (November 2014) departmental declarations of interest in holding Lent Term ‘Week 0’ exams, and will be completed by 23 January 2015.  It will include recommendations about whether an earlier, additional round of sub-board meetings is necessary; and if so, when they should be held.  Person responsible: Hannah Bannister

- Departmental planning for use of the extra term-time week.  Person responsible: Mark Thomson

- Departmental planning of executive programme scheduling.  Person responsible: Mark Thomson

- Planning for alignment of professional services’ business systems with new academic year structure.  Person responsible: individual project board members

# Risks:

# Current risk(s) for highlight are:

| No. | Description | Risk Owner | Countermeasures & Progress | Current status |
| --- | --- | --- | --- | --- |
| 1 | Lack of departmental engagement with planning process | MTT | Progress monitoring to pick up pace of planning across departments; TLC support/guidance with practicalities of structured learning activities during ‘reading week’. | Green |
| 2 | Same information requests made of departments by different projects | MTT/Zoë Saunders-White | RATS project member kept informed of developments on relevant AYR project work streams; vice versa. | Green |

# Issues:

# Current issue(s) for highlight are:

| No. | Description | Issue Owner | Countermeasures | Current status |
| --- | --- | --- | --- | --- |
| 1 | Need to communicate clearly the requirements around ‘Week 6 reading week’ | MTT | Clarify SU expectations; establish extent of departmental discretion in organising extra term-time week. | Amber |
| 2 | Need to begin realignment of School’s business systems under new academic year structure | Ron Riley | This will be kick-started by Ron who has now joined the project board. | Green |

# Lessons Learned in this Period:

| No. | Description |
| --- | --- |