THE LONDON SCHOOL OF ECONOMICS & POLITICAL SCIENCE

LOCAL BUSINESS CONTINUITY PLAN

OFFICE/FUNCTION COVERED BY PLAN:

RESULTS PROCESSING IN JULY

CONTENTS OF PLAN

PART I: PRE-INCIDENT PLANNING						2

PART II: ACTION TO BE TAKEN WHEN DISRUPTION OCCURS	8

FORM 1: SUMMARY OF BUSINESS RECOVERY PRIORITIES

AND RESOURCES REQUIRED FOR RECOVERY FROM

BUSINESS IMPACT ANALYSIS 							11

FORM 2: AREA-SPECIFIC BUSINESS RECOVERY TEAM

TASKS											12

FORM 3: BUSINESS RECOVERY TEAM LEADERS INITIAL ASSESSMENT FORM 								14

FORM 4: INCIDENT LOG								15

THE LONDON SCHOOL OF ECONOMICS AND POLITICAL SCIENCE LOCAL BUSINESS CONTINUITY PLAN

Activity/function/procedure covered by Plan

Results Processing in July (including undergraduate and academic-year taught graduate programmes)

Planning Scenario (common to all areas)

A fire has caused significant damage to a single premises causing the complete loss of a building, contents and IT systems for up to 15 working days. Disruption takes place at a critical time for the disrupted operation.

Critical timing of disruption covered by Plan

The critical time of maximum disruption identified in 2007 Business Impact Analysis (BIA) is the 4-week period from mid-June to mid-July and in particular between: - the end of Week 9 and the Sub-Board meetings in Week 10 - the Sub-Board meetings and the School Board meetings in the following week

PART I: PRE-INCIDENT PLANNING

Purpose

Part I of the Plan identifies:

- the issues that will be addressed in advance so that, should disruption occur, there will be a framework in place to keep the impact within acceptable limits

- the pre-incident actions that will be taken to address these issues and the responsibility for taking the actions; and provides a record of confirmation that the actions have been taken

| ISSUE | AGREED PRE-INCIDENT ACTIONS | RESPONSIBILITY FOR TAKING ACTION | Action Taken? |
| --- | --- | --- | --- |
| 1. ESTABLISH BUSINESS RECOVERY TEAM The primary task of the Team is to keep the impact of the disruption within acceptable limits rather than restore full service | - Key staff needed to manage recovery operations will be identified to form the Business Recovery Team (BRT) - A member of the team will be assigned the role to liaise with the School’s Emergency Management Team (EMT) - BRT members will be assigned clear responsibilities for pre-incident and during incident actions within the Recovery Plan - A list of names and contact details of BRT members will be maintained offsite to be readily available in a recovery situation - All BRT members will be engaged in discussion of detail of implementing pre-incident planning actions - All BRT members will be trained in the actions to be taken in the event of disruption (see Part II) | BRT to comprise the Team Manager (E Lo), Deputy Team Manager (S Banks) and Team Leader (K Evans) EL to liaise with the EMT EL and SB will take collective responsibility for implementing all pre-incident actions in 2-10 below EL EL,SB AND KE EMT in consultation with the Pro-Director of BCP |    |

| 2. IDENTIFY SUBSTITUTE BUSINESS RECOVERY TEAM MEMBERS Who will substitute if key members of the BRT are not available? | The following actions will be taken to ensure that, if one or more members of the BRT are unavailable, recovery will continue: Alternate Recovery Team members will be identified - The agreement of alternates to stand in for BRT members will be obtained and their availability during the critical period of disruption confirmed - Details of BRT substitutes will be kept off site to ensure access | EL in consultation with the Head of SSC EL in consultation with the Head of SSC EL in consultation with the Head of SSC |  |
| --- | --- | --- | --- |

| 3. TRAINING OF BUSINESS RECOVERY TEAM Do all BRT members know what to do in the event of a major disruption to usual service? | - New and alternate members of the BRT will be given business continuity training at the earliest opportunity - Regular refresher sessions will be arranged for regular and stand in BRT members | EMT in consultation with BMT |  |
| --- | --- | --- | --- |

| 4. ACCESS TO PROCEDURES AND EQUIPMENT How will it be ensured that procedures and any vital equipment be accessible? | - A hard copy of critical office procedures will be made available at all times in the LSE Emergency Management Centre (EMC) in Tower 1 and all BRT members will be aware of its location - Electronic access to procedures will be maintained by putting the procedures on USBs (data sticks) which designated members of the BRT will be responsible for - Arrangements will be made with ITS to save key procedural documents in an offsite critical data repository allowing easy access even in the event of a major disruption to IT services - All BRT members will be aware that equipment that may be necessary in an emergency is kept in centrally maintained “battle bags” stored in the EMC | SB/KE SB/KE SB/KE EL/SB/KE |  |
| --- | --- | --- | --- |

| 5. RESUMPTION OF BUSINESS CRITICAL OPERATIONS What are the business recovery priorities for this function? How quickly will critical operations need to be recovered before the impact of disruption becomes unsustainable? | - The recovery priorities identified in the BIA, plus any additional information shown on Form 1 will be confirmed with Director of Business Continuity. These priorities will form the basis of allocation of resources to recover operations - All BRT members will be thoroughly familiar with the information on Form 1 | Definition of recovery priorities confirmed by the BRT with A Webb and D Teed in May 2008 |   |
| --- | --- | --- | --- |

| 6. RESOURCES NEEDED TO RESUME OPERATIONS: STAFF Which staff will be needed to carry out key business recovery operations and how will they be contacted? Will there be any contractual impediments to them working unusual or extended hours in a business recovery situation? | - The staff needed to carry out key roles during the early stages of business continuity will be identified by SB/KE - Contact details for these key staff will be kept out of office at all times in hard copy and on USB sticks - The Head of SSC with HR whether there is a need to change staff contracts to ensure those needed to maintain continuity will work weekends and longer hours in the event of disruption | The Registry Manager (S Rutigliano); and members of the Course and Assessment Team (P Chiazzese, M Johnson, S Johnson and P Lawrence) |  |
| --- | --- | --- | --- |

| 7. RESOURCES NEEDED TO RESUME OPERATIONS: IT Which IT applications are essential to the recovery of operations? How soon will they be restored in the event of a disruption? Note: local plans will be based on IT recovery times set out in the Statement of ICT Recovery These will not become operative until the School’s new co-located Data Centre is operative. Interim plans therefore need to be made, based on a two-week system outage | - Recovery times agreed in the BIA and now enshrined in the Statement of ICT Recovery are shown on Form 1 with any further information subsequently identified by the BRT - A Member of BRT will be appointed to be the contact with MIS in the event of a disruption - All BRT members will familiarise themselves with the recovery times for systems used in the Statement of ICT Recovery - In particular, all BRT members will take note that the ICT Statement of Recovery provides for the restoration of read-only availability of all centrally supported systems within 4 hrs - MIS will be informed that rapid recovery times will apply at weekends and other out-of-hours times at certain business-critical times of year - Workarounds identified in the BIA to manage the non-availability of IT systems will be incorporated into plans for handling the first 4 hrs of a disruption Interim arrangements for two-week system outage Until ICT solutions based on the Statement of Recovery are implemented there is an exposure to loss of IT systems for 2 weeks. Until then, the Form 1 assumption of 24 hrs SITS outage does not apply. Action will be taken prior to the July 2008 results processing period to ensure that impacts will be reduced in the event of a two-week system outage, e.g.: - Responsibility will be allocated to an individual to take appropriate risk mitigation and contingency action throughout the two-week period - Key data will be stored in the critical data repository or on USB - Additional copies of key documentation will be maintained | The BRT has identified that a disruption of 24 hrs is the maximum duration that the team responsible for this process is able to catch up altering the original deadline. Any disruption longer than 24 hrs will mean revisiting of the original schedule. EL BRT/ITS EL EL/SS/KE EL |    |
| --- | --- | --- | --- |

| 8. RESOURCES NEEDED TO RESUME OPERATIONS: WORKING SPACE How many seats will we need to continue our operations if our normal premises are not available? When will an alternative location be available? | - Information from the BIA is given on Form 1 and any further information identified since then - The BRT will note that the EMT will endeavour to provide the number of seats in replacement accommodation identified through BIA within 4 hrs - BRT will note that the precise location of the alternative location will be notified by the EMT to the BRT Manager (see Part II) - BRT will note that EMT will also notify the BRT Manager where the team may temporarily assemble before moving to the replacement accommodation | KE KE KE |  |
| --- | --- | --- | --- |

| 9. RESOURCES NEEDED TO RESUME OPERATIONS: OTHER DEPENDENCIES What other organisational units will need to maintain their actions that contribute to the delivery of your operations? | - Information from the BIA is given on Form 1 and any further information identified subsequently - The BRT will be informed by the EMT of the extent to which other organisational units on which these operations are dependent are able to maintain their contribution to the recovery of these operations (e.g. key staff in MIS and DMU who normally provide technical support to this process) | EMT |  |
| --- | --- | --- | --- |

| 10. ISSUES SPECIFIC TO OFFICE/FUNCTION Issues 1-9 are common to all BRTs The Issues and suggested actions in 10 are specific to this function. They have been identified in discussion with the Director of Business Continuity and will be addressed by the BCT for the function and incorporated into the Office Procedures and Schedule of Recovery Tasks (Form 2) | - Sub-Board meetings Sub-Boards must consider setting contingency meeting dates in case of disruption - Markframe report Recovery at 24 hrs will need the Business Objects “Markframe Report” to be available. This is held on the P Drive which is subject to 3 days recovery. Solutions: - The report will be stored in the critical data repository and on USB so that it will quickly be available in a recovery situation - The ability to process information from saved report will be tested - Markframe paperwork At certain points in the process, only a single paper copy of the Markframe with current annotations is maintained. Appropriate actions will be taken to ensure that the loss of paperwork would be sustainable, including: - Consideration will be given to scanning the annotated Markframe, if feasible - Departments will be instructed to keep a copy of their completed copies before returning them to the SSC - School Board information Consideration will be given to pre-copying/scanning the “suspension of regulations” cases for presentation to School Board, to ensure that this is available for meeting even if premises/systems access is denied on day of meeting - Pass Lists report The Business Objects “Pass Lists Report” will be stored in critical data repository and on USB to ensure that the results can be published even if premises/systems access is denied in day or two leading up to publishing - Results processing and graduation ceremonies – extension The Head of SSC will be asked to consider extending the period between results processing and graduation ceremonies to allow a buffer as - there is already a lot of pressure to meet deadlines - in the event of a crisis happening at this time stress levels could increase significantly A situation causing more than 24 hrs disruption could result in the ceremonies not going ahead, which might have significant credibility issues for the School | SB/KE SB/KE SB/KE SB/KE SB/KE The BRT to raise with the Heqad of the SSC as proposal will require recommendation to the DMT |  |
| --- | --- | --- | --- |

PART II: ACTION TO BE TAKEN WHEN A DISRUPTION TO SERVICE OCCURS

Purpose

Part II of the Plan provides a complete set of instructions for the BRT when an incident and disruption occur.  The actions assume that the pre-incident actions in Part I of the Plan have been implemented.

| STEPS TO BE TAKEN WITHIN FIRST 48 HOURS OF DISRUPTION |  |  |  |
| --- | --- | --- | --- |
| ISSUE | ACTIONS NEEDED | RESPONSIBILITY | Action Taken? |
| 11. MOBILISE BUSINESS RECOVERY TEAM | The EMT will communicate with the BRT Manager to advise them of the current situation and offer guidance on how they should proceed. The situation will be appraised using Form 3 and as appropriate the BRT members will be contacted to set up a meeting at a convenient location. | EL |  |
| 12. INITIATE INCIDENT LOG | The BRT Manager will appoint a “scribe” to record all events and decisions made, including when and by whom actions are taken using Form 4. The scribe will also maintain information on expenses incurred as a result of the disruption (food, accommodation etc.). | EL SB |  |
| 13. OBTAIN EMERGENCY PROCEDURE FOLDER AND “BATTLE BAG” | The BRT members will obtain the procedure folder and ‘’battle bag’’ from the EMC as soon as the team has been contacted to meet and take them to team location. | SB |  |
| 14. ASSESS SITUATION | The BRT will discuss and agree how the situation affects the function. The BRT will refer to the Recovery Requirements on Form 1 and Specific Task Table on Form 2 and assess whether the priorities and information on Forms 1 and 2 are appropriate to respond to the situation. | EL/SB/KE SB/KE |  |
| 15. ASSESS IMPACT OF DATA LOSS | Once the position regarding any loss of recent data from systems is clarified through restoring data from backups taken from a point in time prior to the incident, it will be determined whether or not it is advisable, practical and cost-effective to recreate the lost data. Form 2 contains information regarding manual data recovery. | SB/KE |  |
| 16. COMMENCE RECOVERY AND IMPLEMENT BUSINESS CONTINUITY PLAN | The EMT will keep the BRT informed of the chosen recovery location(s) and the current situation regarding the availability of seats, IT systems, communications and other resources. The BRT will ensure continuity is managed in a way that is appropriate to the recovery resources provided. It is essential to focus only on business critical activities. | EMT SB/KE |  |
| THE FOLLOWING ACTIONS SHOULD INITIALLY BE TAKEN WITHIN THE FIRST 48 HOURS AND WILL CONTINUE DURING THE RECOVERY STAGE UNTIL THE “BUSINESS AS USUAL” STAGE STARTS AFTER 7 DAYS |  |  |  |
| 17. CONTACT AND CO-ORDINATE STAFF | With direction from the EMT, a method(s) will be agreed for contacting staff and the information and guidance that should be provided. Key staff needed to carry out a role during the early stages of business continuity will be agreed. It will also be agreed which staff will not be required for a while. The task of contacting staff will be allocated to one, or more, team members and provide information and guidance, as required. Staff recovery will be co-ordinated, making best use of designated recovery locations, and provide assistance in areas such as arranging transport, authorising expenses costs and sourcing mobile phones or other requirements. | EMT SB/KE EL SB/KE |  |
| 18. RESCHEDULE APPOINTMENTS | Staff will review imminent appointments and ensure these are rescheduled accordingly. | KE |  |
| 19. COMMUNICATE WITH EMERGENCY MANAGEMENT TEAM | BRT will communicate with the EMT to ensure that the most up to date information on the situation is made available and that the timescales identified within the Plan for resource recovery are being met. The EMT will be informed of any problems or issues, as they arise, and provide regular status reports. | EMT/EL |  |
| 20. USE AVAILABLE COMMUNICATION METHODS EFFECTIVELY | If the usual phone capability has been reduced, use will be made of alternative methods to ensure communication continues (e.g. mobiles, home phones, sat phones, home email accounts etc.). | SB/KE |  |
| 21. DETERMINE SCOPE FOR WORKING FROM HOME OR OTHER REMOTE LOCATION | If possible, working from home or another remote location will be implemented to maintain continuity of critical activities, using personal email addresses and mobile phones to communicate. | KE |  |
| THE FOLLOWING ACTIONS SHOULD BE TAKEN AFTER 7 DAYS |  |  |  |
| 22. RECOVER TO BUSINESS AS USUAL STATUS | Under direction from the EMT, there will be a recovery back to “business as usual” status once resources allow, using plans created by the EMT. | EMT/EL |  |
| 23. POST-RECOVERY - ASSESS PAPER LOSS IMPACT | Once the position regarding paper loss is clarified, it will be determined whether or not it is advisable, practical and cost-effective to recreate the lost paperwork. | SB/KE |  |
| 24. POST-RECOVERY - REASSESS IMPACT | Once recovery is complete, the BRT will ask staff to reassess the impact on their work and reprioritise accordingly, considering overtime/use of temporary staff as appropriate to manage any backlogs to return to “business as usual” status. | SB/KE |  |

FORM 1 SUMMARY OF BUSINESS RECOVERY PRIORITIES AND RESOURCES REQUIRED FOR RECOVERY FROM BUSINESS IMPACT ANALYSIS

Purpose: This form provides a summary of the business recovery priorities for the office or function identified in the 2007 Business Impact Analysis and the resources identified in that exercise and subsequently as necessary to enable recovery.

OFFICE/FUNCTION: Results Processing in July

| BUSINESS RECOVERY PRIORITIES FOR OFFICE/FUNCTION |  |  |
| --- | --- | --- |
| Objective | Recovery Time | Notes |
| Ability to process results to meet original/published deadlines without compromising the integrity of the process | Maximum 24 Hours |  |

| MINIMUM SEATING REQUIREMENTS IN ALTERNATIVE LOCATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No of seats at recovery location (desk, PC, phone, printer, photocopier) |  |  |  |  | Notes |
| In 4 hrs | In 24 hrs | In 3 days | In 1 week | In 2 weeks |  |
|  | 8 |  |  |  |  |

| MIS RESOURCE RECOVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| First point at which a resource will be required. Assumes incident occurs at a critical time |  |  |  |  |  |  |  |
| Item | In 4 hrs | In 24 hrs | In 3 days | In 1 wk | In 2wks | In 1 mth | Notes |
| Access to SITS |  |  |  |  |  |  |  |
| Access to Business Objects |  |  |  |  |  |  |  |
| Access to P drive |  |  |  |  |  |  |  |

| NON- MIS RESOURCE RECOVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| First point at which a resource will be required. Assumes incident occurs at a critical time |  |  |  |  |  |  |  |
| Item | In 4 hrs | In 24 hrs | In 3 days | In 1 wk | In 2wks | In 1 mth | Notes |
| Please see section 9 in Part I |  |  |  |  |  |  |  |

| OTHER INFORMATION |  |
| --- | --- |
| Please see section 10 in Part I |  |

FORM 2 AREA-SPECIFIC BUSINESS RECOVERY TEAM TASKS

OFFICE/FUNCTION: Results Processing in July

Purpose: This form is designed to summarise detailed actions the Recovery Team needs to take during an incident to achieve business recovery

| No. | Tasks and Procedures | Respon sibility of: | Phase () |  |  |  When Complete |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 0 to 48 hrs | 3 to 6 days | Over 7 days |  |
| 1 | The actions defined below have been written assuming that the maximum outage of SITS will be up to a maximum of 24 hrs, which should be achievable once the ICT Recovery Strategy is implemented in September 2008. Pending this the BRT will: - Take appropriate risk mitigation and contingency action throughout the 2 week period - Save key data within critical data repository or on memory stick - Maintain additional copies of key documentation | BRT – same for 2 to 12 |  |  |  |  |
| Stage of Procedure - Preparation of Markframes |  |  |  |  |  |  |
| 2 | Consolidated markframes can only be generated after the electronic marksheets for all individual courses have been returned by academic departments and uploaded into SITS by the Exams Office. On the assumption the maximum unavailability of systems will be 24 hrs, suspend the preparation of mark frames until systems and data are available. Advise staff and contacts accordingly. |  |  |  |  |  |
| 3 | Once resources become available, advise staff accordingly, making them aware of any alternative office arrangements. If required, ask staff whether they are available to work overtime (Sundays, evenings, etc.). Offer incentives if appropriate. |  |  |  |  |  |
| 4 | If delivery of mark frames is behind schedule - Consider supplementing staff with SSC and other ARD staff, making effective use of overtime - Reschedule activity in priority order, focusing on preparing paperwork in priority order to meet deadlines for various Sub-Board meetings - Communicate with Chairs of Sub-Boards to identify feasibility of putting back Sub Board meetings that may not receive the required information in time for their scheduled meeting |  |  |  |  |  |
| Stage of Procedure - Meetings of Sub-Boards and School Boards |  |  |  |  |  |  |
| 5 | Continue to provide advice, support and information to Boards. |  |  |  |  |  |
| 6 | Coordinate staff to ensure that they can provide the Board support service at a satisfactory level. |  |  |  |  |  |
| 7 | Take into account that paperwork will not have been distributed prior to Board pre-meetings as it is not delivered until the meeting. Therefore, should the paperwork be unavailable, obtain duplicates (if available) or undertake process to recreate. |  |  |  |  |  |
| Stage of Procedure - Finalising and Publication of Results |  |  |  |  |  |  |
| 8 | Receive mark frames in paper form from Sub-Boards - Await SITS recovery prior to processing - Effectively manage staff and overtime to ensure that any time lost can be caught up quickly |  |  |  |  |  |
| 9 | Focus upon completing preparation in time for School Board Meeting, usually on Thursday/Friday of week after Week 10 (24 hrs suspension of activity should still enable deadline to be met) |  |  |  |  |  |
| 10 | School Board would be difficult to reschedule so priority will be given to the consideration of suspension of regulations cases |  |  |  |  |  |
| 11 | If required, consider publishing provisional results for suspension of regulations cases |  |  |  |  |  |
| 12 | Should LFY be unavailable at time of publishing results then consider utilising paper pass lists on notice boards, notifying results via email or using other methods to communicate results - If systems are unavailable then information should be available in the SSC office in paper form - Communicate with departments, advising of alternative communication methods and/or implications of disruption. Request department assistance with student communication, if appropriate. For example, the academic departments keep records of results for their students, so students could be referred to departments for provisional confirmation of results until such time as the School published official results |  |  |  |  |  |

FORM 3 BUSINESS RECOVERY TEAM LEADERS INITIAL ASSESSMENT FORM

Purpose: This form is to be used to determine the impact of an incident  on individual departments.

OFFICE/FUNCTION: DATE AND NATURE OF INCIDENT

Note: No action should be taken to recover without agreement from the Emergency Management Team.

| Assessment Question | Logged Responses |
| --- | --- |
| Which key staff from your team are unavailable? For how long? |  |
| Which of your normal work areas are inaccessible but intact? |  |
| Which of your normal work areas have been destroyed, damaged or made unusable? |  |
| Which systems and other resources are unavailable (systems, telecomms, utilities)? |  |
| Which of your area’s critical work-in-progress is lost? |  |
| Which of your area’s critical assets and information have been lost? |  |
| What are your team’s priorities and critical activities? |  |
| What deadlines are imminent? |  |
| Which recovery site/location would best satisfy your team’s immediate requirements (designated recovery site, hotel, home working etc.)? |  |
| Which contingency agreements may need to be invoked to support your team’s recovery? |  |
| How many people can work productively at home or mobile for the next few days? |  |

END OF FORM 3

FORM 4 INCIDENT LOG

Purpose: The Incident Log on the following page is designed to be used by the Business Recovery Teams to record any events that occur or decisions taken.  The completion of this log is important for post-incident review.

OFFICE/FUNCTION: DATE AND NATURE OF INCIDENT

Use the sheets as follows: -

- make at least 2 copies of the Incident Log sheet

- make an entry for each significant action, decision or event, noting the date and time

- The team leader will sign off each entry made

- ensure that all staff involved in the recovery use the sheets.

INCIDENT LOG

Team __________________________				Sheet No. ______

| Date | Start Time | End Time | By Whom | Action Taken |
| --- | --- | --- | --- | --- |