Minutes of second EMTEL II Steering Committee meeting

June, 16 2001

NTNU & SINTEF – Trondheim

The second meeting of EMTEL II Steering Committee concludes the Trondheim meeting. The SC meets at the end of plenary work to sum up developments and draft the guidelines for Network activities in the next six months.

Participants	2

Issues to the attention of the SC and related deliberations.	2

Joint Research Fellows - SC meeting	4

Appendix A – Research Fellows timeline, deliverables and timetable amended	6

Minutes will be circulated electronically and stored in the closed access area of EMTEL II Website, at http://www.emtel2.org.

Saturday 16th June 2001, 9:30 – 11:00

Second meeting of EMTEL II Steering Committee, composed by a designated person from each of the seven Centres. In parallel, a meeting of Research Fellows took place. The Fellows report to the SC, and receive feedback from the SC at 10:40.

# Participants

- Dr. Anne-Jorunn Berg 		 	NTNU – SINTEF	Present

- Mr. Marc Bogdanowicz		 	IPTS			Present

- Prof. Jean-Claude Burgelman		SMIT			Apologies

- Ms. Mhiera den Blanken			ASCoR – TNO	Present

for Dr. Valerie Frissen

- Prof. François Pichault		 	LENTIC 		Present

- Prof. Farrell Corcoran			COMTEC		Present

for Prof. Paschal Preston

- Prof. Roger Silverstone 			Media@LSE 		Present

Mr. Lusoli, Research Officer, joined the SC meeting with the purpose of drafting minutes and brief members about administrative concerns. The SC agenda was created in advance of the meeting and finalised in its present form by the integration of issues emerged in the two-day discussion.

# Issues to the attention of the SC and related deliberations.

- Workload distribution in the final phase of the network: key and final deliverables, extension of the contract, main responsibilities

- Key deliverables will be structured in a modular fashion, to the extent allowed by the different methodologies and focus of the projects. Key deliverables will include:

    - an introduction on the European context of the paper - to locate the study as far as possible in a European, comparative perspective, and to indicate the relevance of the project to the wider programme;

    - a section on methodology – in support of ‘localised’ standpoints from which to exercise maximum theoretical leverage;

    - a section on policy (where appropriate) – to reflect and address the multiplicity and complexity of ICT experience in Europe and its possible policy implications.

- The co-ordinating Centre will produce and circulate a common template for the key deliverables.

- Final deliverables will assemble relevant sections from each of the seven key deliverables. Senior researchers at the Centres responsible for the deliverable will edit and preface the deliverables.

- It was recognised that it will be necessary to extend the contract at the end of the Network activities in order to allow the full completion of the work plan.  This  arises as a result the unavoidable delays in recruitment.  An extension would meet the need in the last few months to draft final deliverables when research has been completed in some of the Centres and post-doctoral Fellows have left their position. Resources may be available within individual budgets to marginally extend individual Young Researcher contracts following the appointment of doctoral rather than post-doctoral fellows

- Due to changing circumstances as to the recruitment of Young Researchers, the timeline of the project has changed, and the deadlines fixed in the contract proposal are rescheduled. The titles of final and key deliverables are amended, and the responsibilities for the final deliverables are re-distributed among the Centres. Changes are reported in Annex A to the minutes.

- The Research Fellows will draft detailed work plans of respective research projects and send them to the co-ordinating centre for editing by August, 31 2001.

- Next meeting. Training content (1st Comparative research, 2nd Methodology)

- The next Network meeting will take place in Seville, 14 and 15 March 2002. At this meeting, the Research Fellows will report on their interim research results, receive feedback from the Network and formally draft interim reports by April, 30 2002. The Fellows will send the reports to the co-ordinating centre for editing and submission to the Commission.

- The SC will decide on the training content of the meeting as time comes and research progresses at different Centres.

- Authorship of common written work (if it needs further discussion)

- It is agreed that the Research Fellows are the main authors of the work they produce. They will be acknowledged, depending on the supervision arrangements at different Centres, as sole or principal authors of the Key Deliverables. Senior researchers – or otherwise by agreement – at responsible Centres formally edit the Final Deliverables, and reference Research Fellows as contributors to the edited report.  Publications other than Network publications (key and final deliverables to the EC) will follow the commonly accepted rules in the relevant social science.

- Framework paper: someone to present it, revised, at next meeting. Revision with a view to inform EU policy makers

- The Research Officer will upload a copy of the framework paper to the closed access area of the Website. In addition, he will explore the possibility of discussing the paper online, using typographical co-operative tools.

- Other deliberations

- The penultimate meeting will address again the issue of methodology, and how to draft policy suggestions.

- Dublin (COMTEC) will participate to the drafting of the last two final deliverables.

- A formal agreement will be sought between SMIT and IPTS as to editing the final deliverable Living and Working in the Information Society. IPTS will take the lead in drafting the report, aided by SMIT.

- TNO/ASCoR will formally draft WP7, ICTs and the less able in Everyday Life: modelling impacts and experience with the substantial collaboration of LENTIC.

- The Network co-ordinator will investigate whether – if so how – a representative of the European Commission will participate to the next EMTEL II meeting.

- Satisfaction is expressed with the organisation of the Trondheim meeting.

- Communications from the Research Officer

  - Issues of copyright: publications and conferences.

The research Officer will draft and circulate a standardised phrase of acknowledgement that members of the Network will include in the work they present or publish that relates to the work of the EMTEL II Network.

  - In order to avoid delays in the submission or interim reports to the Commission, local administrators should produce financial statements on time and using the forms provided by the co-ordinating centre.

Members agree to alert their administrators to produce financial statement on time and using the provided forms.

  - The Fellows should produce a report on how their research is progressing, how they were integrated in the academic activities of the training centres and what research training has been provided so far. This allows monitoring progress and fine-tuning the interim reports sent to the Commission.

## The SC agrees, and deliberates that the Fellow produce reports in time for the drafting of the next interim report, not beyond June, 30 2001.

  - Annual report: amendments to work plan and reporting activities in progress.

# Joint Research Fellows - SC meeting

Present: Dr. Thomas Berker, Dr. Myria Georgiou, Ms. Maren Hartmann and Dr. Richard Stevens. The Fellows raise the issue discussed at their own meeting of the issue of authorship. The Fellows agree with the deliberation of the SC as regards authorship, as reported in point three, above, of the minutes. Dr. Georgiou then reports on Fellows’ other concerns about the Network. The SC addresses the concerns.

- Research Fellows: Satisfaction is expressed with the meeting in Trondheim. One hour was an adequate amount of time to present their work and receive feedback.

2. 	Research Fellows: Satisfaction is expressed with the Website, yet Young Researchers need more time to provide content for the ‘Projects’ section. Is it possible to publish Fellows’ papers on the site?

Steering Committee: Publications and papers relevant to Network activities and agenda can be uploaded to the Website.

- Research Fellows: Since the next Network meeting will be in ten months, the Fellows propose to the SC a Fellows’ meeting in the Autumn, to keep in touch with each other’s research and better to co-ordinate research activities. The interim meeting could possibly take place in Amsterdam or Brussels, both central locations, depending on the travel and subsistence costs.

Steering Committee: Great satisfaction is expressed at this initiative of the Fellows: the meeting is agreed. The Research Officer will organise the event on behalf of the SC, liasing with the Research Fellows.

# Appendix A – Research Fellows timeline, deliverables and timetable amended

|  |  |  | 2001 |  |  |  |  |  |  |  |  |  |  |  | 2002 |  |  |  |  |  |  |  |  |  |  |  | 2003 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract |  | 8 |  |  |  | 12 |  |  |  |  |  | 18 |  |  |  |  |  | 24 |  |  |  |  |  | 30 |  |  | 33 |  |  | 36 |  |  | + 3 |
| COMTEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ASCoR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NTNU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDIA@LSE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SMIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LENTIC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#### Structure

Each Thematic project will be the responsibility of a team (IPTS and TNO-ASCoR). The overall project will be the responsibility of the Media@LSE team. COMTEC, as the intellectual and research bridge between the two themes, will have a specific responsibility, together with IPTS and TNO-ASCoR for the final deliverable on policy.

### Projects						Key Deliverables

##### SMIT

Youth and e-commerce: creating consumerism	Digital living and working

IPTS

Ubiquitous computing				What bends the trend? Technological foresight and the socialisation of ubiquitous computing

###### SINTEF/NTNU

ICTs and the flexibility of everyday life		Flexible lives? ICTs and everyday life in Europe

###### COMTEC

The WWW and public communication		‘Content is King’?: public communication and the emergent information society in Europe

###### TNO/ASCoR

ICTs and participation				ICTs and the citizen: policies for participation

###### Media@LSE

Minority media					Minorities and their media in Europe: a comparative study

TNO/ASCoR, with the collaboration of LENTIC

ICTs and the less able in Everyday Life		ICTs and the less able in Everyday Life: modelling impacts and experience

#### Final Deliverables

The Information Society: consumers, citizens and everyday life (a summary report of the substantive findings of the research programme, edited by Media@LSE)

The Information Society: methods and methodologies (edited by LENTIC)

The Information Society: policy prospects (edited by COMTEC, SMIT and TNO-ASCoR)

Living and Working in the Information Society (edited by IPTS, SMIT and NTNU)

Inclusion and Exclusion in the Information Society (edited by TNO-ASCoR, Media@LSE and LENTIC)

#### Schedule

Time (months after project start) and deadline	Deliverable

15  –  1 September 2001			Detailed work plan 		All Centres

24  –  1 May 2002			Interim WP reports		All Centres

36  –  1 May 2003			Draft Key Deliverables		All Centres

+3  –  1 August 2003			Key Deliverables		All Centres

+6  –  1 October 2003			Final Deliverables		All Centres